## PI3
2021.3 Program Incremental Planning |  |  |  | Project Name
IT Data Engineering / NextGen Data Warehouse
| Priority | Board | PI Goals | Project Name | IT EQA Required | Contact outside of ITDE | Assignee | From | To | Dependencies | Issues/Blocks | Status | Comments
1 | Medium | ITDE | Enhancement: Refactor qualtrics export job / reduce delivery times to improve NPS |  | N | Kate Wiggins | ? |  |  | CEX: Work with us to define scope
1 | Low | NXTG | Enhancement: Replace Planitas with Accelya data |  | N | Richard Johns | ? |  |  | Ashley to follow up Sai |  |  | Ashley to talk to Sai
1 | Medium | ITDE | Export Job: Loyalty Enhancements (Additional ancillaries) | Mayflower | Y | Jeff Krenn / Diane | ? |  |  | None |  |  | Ashley to follow up
1 | Medium | ITDE | Integrate: MasFlight |  | N | Matthew Urbanek | ?
2 | Low | ITDE | Integration: Climacell |  | N | Bob Ohare | ? |  |  | Airports CEX: Obtain source data
2 | Low | ITDE | Integration: Comply 365 |  | N | Lynn Ford | ? |  |  | None |  |  | Audit committee wants to better understand compliance. Who's looking @ articles on C365?
2 | Low | NXTG | Integration: CS 100 Data (Ground Ops Team) |  | N | Suzie Lam | ? |  |  | None
2 | Medium | ITDE | Integration: Point of Sale info from flight |  | N | Ed Baklor | ? |  |  | Internal dependency: get information about source data |  |  | 2 Sprints development - Ashley to follow up
2 | Low | NXTG | Integration: Preference Center |  | N | N/A | ? |  |  | None
3 | Medium | ITDE | Integration: National Weather Service feeds |  | N | Sai Ravuru | Shivani |  |  | Domains: Publish SWIM messages to East US 2
3 | Medium | ITDE | Integration: Talis data (inflight entertainment @ the seat level) |  | N | ?? | ?
3 | High | NXTG | Perform UAT: Inventory Optimizer P2P |  | N | Backlog | ? |  |  | None
| High | ITDE | Enhancement: OE Report |  | N | Satish / Crew domain team | Sergey | PI-4 | PI-4 | None
3 | Low | ITDE | POC: Create data exposures for export jobs |  | N | N/A | ? |  |  | None
3 | Low | NXTG | Point-to-point: Axciom |  | N |  | ? |  |  | None
3 | Low | NXTG | Point-to-point: Customer Hub |  | N | N/A | ? |  |  | None
| High | ITDE | UAT for Vendor Spend Analytics Reports |  | N | Ciby Fernandez | ? | Sprint 3.2 | Sprint 3.2 | SAP file availability on schedule basis
1 | Highest | NXTG | Integrate: Responsys Load New Subscribers | Next Gen | Y | N/A | Abhishek | Sprint 3.1 | Sprint 3.1 |  |  |  | PREF_CENTER_LIST_EXPORT
1 | High | NXTG | Integration: Aerodata | Next Gen | Y | Dave Reynolds | Abhishek | Sprint 3.1 | Sprint 3.2 | None
1 | Low | ITDE | Integration: Airship |  | N | Kanwar ? | Abhishek | Sprint 3.4 | Sprint 3.6 | Domains: Airship data needs to be available in blob |  |  | *Ashley to follow up on source data availability*
1 | Medium | ITDE | Enhancement: SQ Report |  | N | Satish / Crew domain | Sergey |  |  | Not Known |  | DONE
3 | Low | NXTG | Miscellaneous data request: Replicate Survey Analysis Table to Snowflake (Testing Purposes) |  | N | N/A | Abhishek | Sprint 3.3 | Sprint 3.3 | None
4 | Medium | NXTG | QA Support: CASS | Next Gen | Y | Abhishek | Abhishek | Sprint 3.1 | Sprint 3.2 | None
| Medium | NXTG | UAT Support: Aerodata | Next Gen | Y | Dave Reynolds | Abhishek | Sprint 3.3 | Sprint 3.4 | None
1 | Low | NXTG | Decommission: SurveyAnalysis Reference tables |  | N | Kate Wiggins | Alex | Sprint 3.2 | Sprint 3.3 | None |  |  | Ashley to follow up with Kate
1 | High | ITDE | Enhancement: Curated data model for Loyalty |  | N | Pyper Ribble | Alex | Sprint 3.4 | Sprint 3.5 | Loyalty: Refine scope & give us feedback
1 | High | NXTG | Enhancement: Refactor Qualtrics Participant file | Next Gen | Y | Kate Wiggins | Alex | Sprint 3.1 | Sprint 3.1 | CEX: Work with us to define scope |  |  | ** Fix Fivetran & Qualtrics connector
4 | High | NXTG | QA Support: Refactor Qualtrics Participant file | Next Gen | Y | Kate Wiggins | Alex | Sprint 3.2 | Sprint 3.3 | None |  |  | ** Fix Fivetran & Qualtrics connector
| Highest | NXTG | UAT Support: AQD |  | N | Jacob Hillery | Alex | Sprint 3.1 | Sprint 3.1 | None
1 | High | NXTG | Integration: Aircom (APU on/off messages) |  | N | Emir or Chuck Cook | Prajakta | Sprint 3.6 | PI-4 | None
1 | Highest | ITDE | Integration: APIS messages | TOPS | Y | Jeanny Patterson / Ranjit Raveendran | Arun | Sprint 3.4 | Sprint 3.5 |  |  |  | Ashley to follow up
2 | Medium | ITDE | Integration: BIDT (Billing Information Data Tapes) | Project Connie | Y | Maria Taylor | Arun | Sprint 3.1 | Sprint 3.2 | None
2 | Medium | NXTG | Integration: CrewQual |  | N | Satish | Arun | Sprint 3.5 | Sprint 3.6 | None
4 | Highest | ITDE | QA Support: 15 Below | EC261 | Y | Kanwar / Megha | Arun | Sprint 3.1 | Sprint 3.2
4 | High | ITDE | QA Support: Baggage Domain | Next Gen | Y | Arun | Arun | Sprint 3.3 | Sprint 3.4 | None
| Medium | ITDE | QA Support: BIDT (Billing Information Data Tapes) |  | N | Maria Taylor | Arun | Sprint 3.2 | Sprint 3.3 | None
4 | Highest | ITDE | Export Job: 15 Below - Rework | EC261 | Y | Kanwar / Megha | Arun | Sprint 3.4 | Sprint 3.4
1 | Highest | NXTG | Decommission: Legacy Snowflake databases Phase 1 |  | N | N/A | Ashley | Sprint 3.1 | Sprint 3.1 | None
1 | Highest | NXTG | Enhancement: Consolidate reference data in Snowflake |  | N | N/A | Ashley | Sprint 3.2 | Sprint 3.3 | None
2 | Low | ITDE | Integration: Build self-service data pipeline (Transtats) |  | N | N/A | Ashley | Sprint 3.4 | Sprint 3.5 | None
3 | Highest | ITDE | Miscellaneous data request: Interaction Domains Audit |  | N | Dee Dee Gardner | Ashley | Sprint 3.1 | Sprint 3.1 | None
3 | Highest | ITDE | Miscellaneous data request: Interaction One time Data Extract |  | N | Dee Dee Gardner | Ashley | Sprint 3.1 | Sprint 3.1 | None
1 | Highest | NXTG | Decommission: Legacy Snowflake databases Phase 2 |  | N | N/A | Ashley | Sprint 3.4 | Sprint 3.6 | None
1 | Highest | NXTG | Exercise: Test FIT on a Sunday with BI team |  | N | Luice Bloom | Ashley/Subbu | Sprint 3.4 | Sprint 3.4
1 | High | NXTG | Administrative: Create Product Quality Metrics on Snowflake Adoption |  | N | N/A | Kamran | Sprint 3.1 | Sprint 3.1
1 | Highest | NXTG | Administrative: On-prem inventory list |  | N | N/A | Kamran | Sprint 3.1 | Sprint 3.1 |  |  |  | All SSIS jobs
1 | Highest | NXTG | Administrative: Test "persist docs" across all schemas & turn it on in production |  | N | N/A | Kamran | Sprint 3.2 | Sprint 3.2 | Allows you to write desc table & see docs in Snowflake
2 | Medium | ITDE | Integration: Navigation data in prod |  | N | Chris Menchion | Kamran | Sprint 3.1 | Sprint 3.2 | Navigation team: finish UAT
3 | High | NXTG | Integration: Workforce Planning / Datamatics (project Maple will replace these) |  | N | Rishi / Dave Thorpe (Maple) | Krupa | Sprint 3.4 | Sprint 3.6 | Ashley to meet with Rishi & co |  |  | Fuels a lot of analysis around staffing - Ashley to meet with Rishi & co
3 | Medium | NXTG | Perform UAT: OTP (On Time Performance for Partner Airlines) |  | N |  | Krupa | Sprint 3.2 | Sprint 3.3
2 | Medium | ITDE | Integration: PBS Award data from NavBlue |  | N | Satish / Crew domain team | Sergey | PI-4 | PI-4 | Crew Services: Resource availability for UAT
1 | Highest | ITDE | Integrate: Ops Status from HelloJetBlue |  | N | N/A | Nilesh | Sprint 3.2 | Sprint 3.3
2 | High | ITDE | Integration: ASAPP | TBD | Y | Justin Thompson | Nilesh | Sprint 3.4 | Sprint 3.5 | CEX: Enable access to the source data |  |  | ASAPP - This is our future customer support platform. The data will give us insights into crewmember interactions with customers
4 | Medium | NXTG | QA support: AQD P2P |  | N |  | Nilesh | Sprint 3.1 | Sprint 3.2 | None
4 | Highest | ITDE | QA Support: Even More Space Upsell email updates (including aircraft updates) | Next Gen | Y | Kyle Gehring & Brian Mazur | Nilesh | Sprint 3.1 | Sprint 3.2 | None
| Highest | ITDE | UAT Support: AQD to NASA |  | N | Shari Thomas | Nilesh | Sprint 3.2 | Sprint 3.2 | None |  |  | AQD point to point to NASA - Jetblue needs to send voluntary pilot error reports from our safety database (AQD) to NASA. These reports will be loaded into their database and aggregated for research and analysis. NASA has the repository of all the incidents
2 | High | ITDE | UAT Support: ASAPP |  | N | Justin Thompson | Nilesh | Sprint 3.5 | Sprint 3.5 | CEX: Enable access to the source data |  |  | ASAPP - This is our future customer support platform. The data will give us insights into crewmember interactions with customers
1 | Highest | NXTG | Export Job: CCURE to SAP |  | N | Shari Thomas | Prajakta | Sprint 3.4 | Sprint 3.5 |  |  |  | Identify the crewmembers, whose badge ids are expiring within 90 days, 60 days and 30 days, send email notification to their crew leaders to act upon.
1 | Highest | ITDE | Export Job: Dunkin Trueblue Partnership emails | Next Gen | Y | Brian Mazur & Nicholas Meluso | Prajakta | Sprint 3.1 | Sprint 3.1 | Loyalty: Ensure delivery of CashStar sample files
2 | High | ITDE | Integration: Historical pricing from Fares Manager |  | N | RM / Pricing team | Prajakta | Sprint 3.2 | Sprint 3.3 | Revenue team: Send us the location of the historical files
4 | Highest | ITDE | QA Support: Dunkin Trueblue Partnership emails | Next Gen | Y | Brian Mazur & Nicholas Meluso | Prajakta | Sprint 3.2 | Sprint 3.3 | None
| Highest | NXTG | QA support: TOPS | TOPS | Y | Wai Sze Lok (PM) | Priya | Sprint 3.4 | Sprint 3.6 | None
1 | Highest | NXTG | Enhancement: BP Mart / Tops data source development | TOPS | Y | Matthew Urbanek | Priya/Krupa | Sprint 3.1 | Sprint 3.3
1 | High | ITDE | Enhancement: Curated data model for Revenue |  | N | RM | Reid | Sprint 3.5 | Sprint 3.6 | None
1 | Highest | NXTG | Enhancement: Refactor data model for ACS to match with batch |  | N |  | Reid | Sprint 3.3 | Sprint 3.3
1 | Highest | NXTG | Enhancement: Refactor data model for PNR to match with batch |  | N | N/A | Reid | Sprint 3.1 | Sprint 3.1
1 | Highest | NXTG | Enhancement: Refactor data model for ticket to match with batch |  | N |  | Reid | Sprint 3.2 | Sprint 3.2
3 | High | NXTG | POC: Automate dbt Run in Stage |  | N | N/A | Reid | Sprint 3.4 | Sprint 3.4 | None
1 | Highest | ITDE | Enhancement: Build 50 custom data tests (based on matrix partner inputs & our own ideas) |  | N | N/A | Reid/Kamran | Sprint 3.1 | Sprint 3.5
3 | Medium | NXTG | Support UAT: OTP (On Time Performance for Partner Airlines) |  | N |  | Reid/Kamran | Sprint 3.2 | Sprint 3.3
| Medium | ITDE | Enhancement: PCC Time Zone Reference Tables |  | N | Hogan Antia | Sakshi | Sprint 3.1 | Sprint 3.1
2 | Highest | ITDE | Integration: Avaya CMS data modeling & curated view |  | N | Justin Thompson | Sakshi | Sprint 3.3 | Sprint 3.5 | CEX: Work with us to define scope & provide feedback
3 | High | ITDE | Integration: Vendor Spend Analytics Reports |  | N | Ciby Fernandez | Sakshi | Sprint 3.1 | Sprint 3.1 | SAP file availability on schedule basis
3 | Highest | NXTG | Perform UAT: Gender identity cutover |  | N | CJ Abel | Sakshi | Sprint 3.2 | Sprint 3.5
2 | Highest | ITDE | UAT Support for Avaya CMS data modeling & curated view |  | N | Justin Thompson | Sakshi | Sprint 3.5 | Sprint 3.6 | CEX: Work with us to define scope & provide feedback
| High | ITDE | UAT Support: Vendor Spend Analytics Reports |  | N | Ciby Fernandez | Sakshi | Sprint 3.2 | Sprint 3.2 | SAP file availability on schedule basis
2 | High | NXTG | Integration: Build "curated" FlightPlanningData view |  | N | Dave Reynolds | Sandhya | Sprint 3.4 | Sprint 3.6
2 | Highest | ITDE | Integration: PeopleFluent (6 or 7 files) |  | N | TA team | Sandhya | Sprint 3.1 | Sprint 3.2 |  |  |  | Sucess factor - Historical Loads
3 | Highest | ITDE | Integration: Union SuccessFactors + PeopleFluent |  | N | TA team | Sandhya | Sprint 3.3 | Sprint 3.3
4 | High | ITDE | QA Support: passengers_fact table | Next Gen | Y | Ben | Sandhya | Sprint 3.4 | Sprint 3.5 | None
| Highest | ITDE | UAT Support: Bag Tracking for Fare Options 2.1 |  | N | RM - Elaine Kuo | Sandhya | Sprint 3.1 | Sprint 3.2 | None
2 | Highest | ITDE | Integration: Build Reference Domain Report |  | Y | Ref Domain (Peterson/Tami) | Sandhya | Sprint 3.1 | Sprint 3.5 |  |  |  | Sucess factor - Historical Loads
2 | Highest | ITDE | QA Support: Ancillary Fact for GDS bookings (EMD) |  | Y | QA Team | Sandhya | Sprint 3.1 | Sprint 3.2 |  |  |  | Sucess factor - Historical Loads
1 | Medium | ITDE | Enhancement: Flight DRO report |  | N | Satish / Crew domain team | Sergey | Sprint 3.6 | Sprint 3.6 | dependent on Rainmaker Crew Pay, and FLICA
1 | High | NXTG | Integration: Archive Query History on a schedule |  | N | N/A | Sergey | Sprint 3.1 | Sprint 3.1
2 | Medium | ITDE | Integration: Check airmen list |  | N | Satish / Crew domain team | Sergey | Sprint 3.2 | Sprint 3.2 | None
2 | Medium | NXTG | Integration: CrewPay |  | N | Satish | Sergey | Sprint 3.4 | Sprint 3.4 | None
2 | Medium | ITDE | Integration: FLICA |  | N | Satish / Crew domain team | Sergey | Sprint 3.3 | Sprint 3.3 | None
3 | Low | ITDE | Enhancement: Inlight DRO report |  | N | N/A | Sergey | Sprint 3.5 | Sprint 3.5 | None
4 | Medium | ITDE | QA Support: Inflight Duty Day, 24/7, and Pairing Scheduled service reports |  | N | Satish / Crew domain team | Sergey |  |  | Crew Services: Resource availability for UAT
| High | NXTG | Enhancement: improve dbt models performance |  | N |  | Sergey
2 | High | ITDE | Integration: i6 | TBD | Y | Chris Gottlieb | Shivani | Sprint 3.5 | Sprint 3.6
2 | Highest | ITDE | Integration: Kiosk data |  | N | Boris | Shivani | Sprint 3.3 | Sprint 3.4 | ITPE: Grant us access to the source database
3 | Highest | ITDE | Point-to-point: FDX to IATA |  | N | Shari Thomas | Shivani | Sprint 3.1 | Sprint 3.1 | None
| Highest | ITDE | UAT Support: FDX to IATA |  | N | Shari Thomas | Shivani | Sprint 3.1 | Sprint 3.2 | None
1 | Highest | NXTG | Enhancement: Implement FIT for batch feeds |  | N | Lucie Bloom | Subbu | Sprint 3.1 | Sprint 3.1 | None
2 | Highest | ITDE | Integration: IFSA (Voucher Phase 2 Requirements) | IFSA | Y | Steve Shultz | Subbu | Sprint 3.4 | Sprint 3.5 | Domains: Publish messages to East US 2
4 | Medium | ITDE | QA Support: Loyalty | Next Gen | Y | Pyper Ribble | Subbu | Sprint 3.2 | Sprint 3.3 | None
4 | Highest | ITDE | QA Support: Opaque emails for Travelbank |  | N | Alisha Richardson | Subbu | Sprint 3.1 | Sprint 3.1
| Highest | ITDE | UAT Support: eGOR RT rollout |  | N | Juliette Parker / Suganya | Subbu | Sprint 3.3 | Sprint 3.6
| High | ITDE | Integration: Contact Analyzer |  | N | Corey | Subbu | Sprint 3.3 | Sprint 3.4
3 | Highest | ITDE | Integration: SAP (HVR) |  | N | Mukarram | TBD - VisualBI |  |  | Architecture & infrastructure: Complete HVR implementation
3 | Highest | NXTG | Integration: Trax (HVR) | Next Gen | Y | Tech Ops | Vibhuti | Sprint 3.2 | Sprint 3.5
3 | High | ITDE | SSIS: Automate IO (Inventory Optimizer) - Scheduled Stats File movement |  | N | Rose Hsu | Vibhuti | Sprint 3.1 | Sprint 3.1
4 | Highest | NXTG | Point-to-point: Inventory Optimizer |  | N | Rose Hsu | Vibhuti | Sprint 3.5 | PI-4 | None
4 | Highest | ITDE | QA Support: Accelya | Project Connie | Y | Matthew Jacinovich | Vibhuti | Sprint 3.1 | Sprint 3.1 | None
4 | High | ITDE | QA Support: EMD ASR | EMD | Y | Rich Smith | Vibhuti | Sprint 3.1 | Sprint 3.1 | None